## Plan
Sr. No. | Date | Task | Days Allocated for task | Resource Link | Task Status | Progress
1 | 17th - 19th | JS basics and revisiting Vue.JS stuff | 3 | For JS: Basic section of https://www.tutorialrepublic.com/javascript-tutorial/ For Vue.JS: Official Vue.JS tutorial: https://vuejs.org/tutorial/#step-1 | In Progress | 1
2 | 22nd - 25th | Based on his understanding and interview on 22nd, will either give him this timeframe to improve more on leetcode or start builing components in Nivi | 4 | There are many references for interview questions. For coding, maybe can repeat questions I and Mit asked plus some are good over here: https://www.interviewbit.com/javascript-interview-questions/#output-of-following-code-1 | Not Started | 0
3 | 26th - 06th | Task on dashboard | 8 | 1. Create new menu with name 'offerings-improved' 2. Copy-paste all code from offerings-management 3. Make offerings-management panels/sections expand/collapse toggle 4. Keep proper validations and expand if there is any error in input 5. Create an API to save this new data on the stage DB I will create some new temp tables for him to store and load data. If time permits, will ask him to have one more section of offering-messages, which will have side-by-side 2 message sets storing different values and their validations | Not Started | 0
*For Leetcode: He should everyday solve atleast 5 questions of easy level. I will myself solve the questions first and then give him, and then discuss next day. If he does this regularly without skipping saturday-sunday, he would have solved 100+ questions.

## LeetCode questions
Sr. No. | Topic | Question | Question Link | Date
1 | Arrays | Two Sum | https://leetcode.com/problems/two-sum/ | 16/08/2022
2 | Arrays | Remove Duplicates from Sorted Array | https://leetcode.com/problems/remove-duplicates-from-sorted-array/
3 | Arrays | Remove Element | https://leetcode.com/problems/remove-element/